## Slide 1: INTELLIGENT TOURIST SYSTEM MINI PROJECT Department of MCA,MES College of Engineering,Kuttippuram
PREPARED BY
SHIMA JALEEL (MES22MCA-2056)
3rd NOVEMBER 2023

## Slide 2
GUIDED BY
MR. NOWSHAD CV
MASTER OF COMPUTER APPLICATIONS
MES COLLEGE OF ENGINEERING , KUTTIPPURAM

## Slide 3: CONTENTS
Overview
Functionality
Product Backlog
Project Plan
Sprint
DFD
Development Environment

## Slide 4: OVERVIEW
The Project is entitled as “Intelligent Tourist System”. Smartphones are inevitable nowadays; this project is mainly for tourist who faces many difficulties in their journey.
This project will help to improve the existing navigation system in smartphone by solving the tourist confusions while travelling many new places also this project benefits in many aspects.
This mobile application project is very beneficial, user friendly, quicker and flexible with many future oriented ideas. This mobile application is built using advanced Software that can work in many platforms not only in android OS.

## Slide 5
MODULES
ADMIN
  LOGIN
  MANAGE PLACES
  VIEW USER PROFILES
  USER FEEDBACK
USER
    LOGIN
    REGISTER
    VIEW/SEARCH PLACES
    SEND FEEDBACKS

## Slide 6: PRODUCT BACKLOG
ID | PRIORITY | SIZE (Hours) | SPRINT | STATUS | NAME
1 | Medium | 3 | 1 | Planned | Form Design
2 | Medium | 1 |  | Partially Completed | Admin Panel
3 | High | 4 | 2 | Planned | Table Design
4 | High | 23 |  | Planned | Coding
5 | Medium | 4 | 3 | Planned | Testing Data
6 | High | 6 |  | Planned | Output Generation

## Slide 7: PROJECT PLAN
ID | TASK NAME | START DATE | END DATE | PROJECT HOURS | STATUS
1 | Sprint 1 | 15/09/2023 | 12/10/2023 | 13 | Partially Completed
2 | Sprint 2 | 13/10/2023 | 03/11/2023 | 14 | Planned
3 | Sprint 3 | 08/11/2023 | 30/11/2023 | 14 | Planned

## Slide 8: SPRINT PLAN
SPRINT 1
Backlog Item | Status and Completion date | Original Estimate in hours | Day 1 15/09 | Day 2 20/09 | Day 3 21/09 | Day 4 28/09 | Day 5 29/09 | Day 6 04/10 | Day 7 05/10 | Day 8 06/10 | Day 9 11/10 | Day 10 12/10
Form Design | 15/09/2023 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table Design | 28/09/2023 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 06/10/2023 | 6 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 0 | 0
Testing & Validation | 12/10/2023 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Total |  | 13 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1

## Slide 9: SPRINT PLAN
SPRINT 2
Backlog Item | Status and Completion date | Original Estimate in hours | Day 1 13/10 | Day 2 18/10 | Day 3 19/10 | Day 4 20/10 | Day 5 25/10 | Day 6 26/10 | Day 7 27/10 | Day 8 01/11 | Day 9 02/11 | Day 10 03/11
Form Design | 13/10/2023 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Table Design | 18/10/2023 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Coding | 01/11/2023 | 8 | 0 | 0 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 0
Testing & Validation | 03/11/2023 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2
Total |  | 14 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2

## Slide 10: SPRINT PLAN
SPRINT 3
Backlog Item | Status and Completion date | Original Estimate in hours | Day 1 08/11 | Day 2 09/11 | Day 3 10/11 | Day 4 15/11 | Day 5 16/11 | Day 6 17/11 | Day 7 22/11 | Day 8 23/11 | Day 9 24/11 | Day 10 29/11 | Day 11 30/11
Coding | 01/11/2023 | 9 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0
Testing & Validation | 03/11/2023 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1
Total |  | 14 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1

## Slide 11: DFD LEVEL 0
Admin
User
Intelligent Tourist System
Database

## Slide 12
View Feedback
User Profiles
Manage Places
Login
Admin
Places
Login
User
Feedback
LEVEL 1

## Slide 13
Add Feedback
View Places
Login
Registration
User
Places
Feedback
Login
User
LEVEL 2

## Slide 14: DEVELOPMENT ENVIRONMENT
HARDWARE SPECIFICATION
Processor : intel core i3 Processor
Hard Disk : 40GB HDD4
RAM : 8GB RAM
SOFTWARE SPECIFICATION
Operating System : Windows
Front End : DART
Framework : FLUTTER
Backend : PHP
Browser : Google Chrome , Mozilla Firefox, Microsoft Edge .

## Slide 15: Thank you